## Parameters
Project: | DBL Webtech
Tasks |  | estimated effort(hours) | Participants |  | Budget
Task1 | Sprint Planning | 1:00 | Student1 | David | 140:00
Task2 | Daily Scrum | 1:00 | Student2 | Georgi | 140:00
Task3 | Sprint Review | 1:00 | Student3 | Jeroen | 140:00
Task4 | Lectures/Plenary meetings | 1:00 | Student4 | Julek | 140:00
Task5 | Sprint Task 0. Administration | 1:00 | Student5 | Sasha | 140:00
Task6 | Sprint Task 1. Create website | 1:00 | Student6 | Theo | 140:00
Task7 | Sprint Task 2. Create visualization 1 | 1:00 |  | Total budget | 1900-02-03
Task8 | Sprint Task 3. Allow for data upload | 1:00
Task9 | Sprint Task 4. Create draft interim report | 1:00
Task10 | Sprint Task 5. Create visualization 2 | 1:00
Task11 | Sprint Task 6. Add interactions | 1:00
Task12 | Sprint Task x.x
Task13 | Sprint Task x.x
Task14 | Sprint Task x.x
Task15 | Sprint Task x.x
Task16 | Sprint Task x.x
Task17 | Sprint Task x.x
Task18 | Sprint Task x.x
Task19 | Sprint Task x.x
Task20 | Sprint Task x.x
| total estimated effort | 0.45833
| remaining budget: | 1900-02-02 13:00
Formulas:
Budget = SUM(G5:[Budget, row above])
estimated effort(hours) = SUM(C5:[estimated effort(hours), row above])
estimated effort(hours) = G11-[estimated effort(hours), row above]

## David
Time registration | David
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning | 1:00 | 2:00
| Daily Scrum |  | 1:00
| Sprint Review |  | 0:30
| Lectures/Plenary meetings | 1:00
| Sprint Task 0. Administration | 1:30 | 2:30
| Sprint Task 1. Create website |  | 6:00
| Sprint Task 2. Create visualization 1 | 2:00 | 4:00
Sprint Task 3. Allow for data upload
| Sprint Task 4. Create draft interim report |  | 0:30
Sprint Task 5. Create visualization 2
Sprint Task 6. Add interactions
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
|  | 0.22917 | 0.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.22917 | 0.91667 | 0.91667 | 0.91667 | 0.91667 | 0.91667 | 0.91667 | 0.91667 | 0.91667 | 0.91667
| remaining hours | 1900-01-04 14:30 | 1900-01-03 22:00 | 1900-01-03 22:00 | 1900-01-03 22:00 | 1900-01-03 22:00 | 1900-01-03 22:00 | 1900-01-03 22:00 | 1900-01-03 22:00 | 1900-01-03 22:00 | 1900-01-03 22:00

## Georgi
Time registration | Georgi
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning | 1:00 | 1:30
| Daily Scrum | 0:30 | 1:00
| Sprint Review |  | 0:30
| Lectures/Plenary meetings | 1:00
| Sprint Task 0. Administration | 2:00 | 3:00
Sprint Task 1. Create website
Sprint Task 2. Create visualization 1
Sprint Task 3. Allow for data upload
| Sprint Task 4. Create draft interim report |  | 0:30
Sprint Task 5. Create visualization 2
Sprint Task 6. Add interactions
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
|  | 0.1875 | 0.27083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.1875 | 0.45833 | 0.45833 | 0.45833 | 0.45833 | 0.45833 | 0.45833 | 0.45833 | 0.45833 | 0.45833
| remaining hours | 1900-01-04 15:30 | 1900-01-04 09:00 | 1900-01-04 09:00 | 1900-01-04 09:00 | 1900-01-04 09:00 | 1900-01-04 09:00 | 1900-01-04 09:00 | 1900-01-04 09:00 | 1900-01-04 09:00 | 1900-01-04 09:00

## Jeroen
Time registration | Jeroen
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
Sprint Planning
| Daily Scrum | 4:00 | 4:00
Sprint Review
| Lectures/Plenary meetings | 2:00
| Sprint Task 0. Administration | 0:30
Sprint Task 1. Create website
| Sprint Task 2. Create visualization 1 | 2:00 | 3:00
Sprint Task 3. Allow for data upload
Sprint Task 4. Create draft interim report
Sprint Task 5. Create visualization 2
| Sprint Task 6. Add interactions |  | 1:00
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
|  | 0.35417 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.35417 | 0.6875 | 0.6875 | 0.6875 | 0.6875 | 0.6875 | 0.6875 | 0.6875 | 0.6875 | 0.6875
| remaining hours | 1900-01-04 11:30 | 1900-01-04 03:30 | 1900-01-04 03:30 | 1900-01-04 03:30 | 1900-01-04 03:30 | 1900-01-04 03:30 | 1900-01-04 03:30 | 1900-01-04 03:30 | 1900-01-04 03:30 | 1900-01-04 03:30

## Julek
Time registration | Julek
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning | 1:00 | 2:00
| Daily Scrum | 0:30 | 1:00
| Sprint Review |  | 0:30
| Lectures/Plenary meetings | 1:00
| Sprint Task 0. Administration | 1:30 | 2:00
| Sprint Task 1. Create website | 6:00 | 5:00
Sprint Task 2. Create visualization 1
Sprint Task 3. Allow for data upload
Sprint Task 4. Create draft interim report
Sprint Task 5. Create visualization 2
Sprint Task 6. Add interactions
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
|  | 0.41667 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.41667 | 0.85417 | 0.85417 | 0.85417 | 0.85417 | 0.85417 | 0.85417 | 0.85417 | 0.85417 | 0.85417
| remaining hours | 1900-01-04 10:00 | 1900-01-03 23:30 | 1900-01-03 23:30 | 1900-01-03 23:30 | 1900-01-03 23:30 | 1900-01-03 23:30 | 1900-01-03 23:30 | 1900-01-03 23:30 | 1900-01-03 23:30 | 1900-01-03 23:30

## Sasha
Time registration | Sasha
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning | 1:00 | 2:00
| Daily Scrum |  | 1:00
| Sprint Review |  | 0:30
| Lectures/Plenary meetings | 1:00
| Sprint Task 0. Administration | 2:00 | 1:00
Sprint Task 1. Create website
Sprint Task 2. Create visualization 1
| Sprint Task 3. Allow for data upload | 3:00 | 8:00
Sprint Task 4. Create draft interim report
Sprint Task 5. Create visualization 2
Sprint Task 6. Add interactions
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
|  | 0.29167 | 0.52083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.29167 | 0.8125 | 0.8125 | 0.8125 | 0.8125 | 0.8125 | 0.8125 | 0.8125 | 0.8125 | 0.8125
| remaining hours | 1900-01-04 13:00 | 1900-01-04 00:30 | 1900-01-04 00:30 | 1900-01-04 00:30 | 1900-01-04 00:30 | 1900-01-04 00:30 | 1900-01-04 00:30 | 1900-01-04 00:30 | 1900-01-04 00:30 | 1900-01-04 00:30

## Theo
Time registration | Theo
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task
| Sprint Planning | 1:00 | 2:00
| Daily Scrum | 0:30 | 1:30
| Sprint Review |  | 0:30
| Lectures/Plenary meetings | 1:00
| Sprint Task 0. Administration | 2:00 | 4:00
Sprint Task 1. Create website
Sprint Task 2. Create visualization 1
| Sprint Task 3. Allow for data upload | 2:00 | 1:00
Sprint Task 4. Create draft interim report
Sprint Task 5. Create visualization 2
Sprint Task 6. Add interactions
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
Sprint Task x.x
|  | 0.27083 | 0.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours spent | 0.27083 | 0.64583 | 0.64583 | 0.64583 | 0.64583 | 0.64583 | 0.64583 | 0.64583 | 0.64583 | 0.64583
| remaining hours | 1900-01-04 13:30 | 1900-01-04 04:30 | 1900-01-04 04:30 | 1900-01-04 04:30 | 1900-01-04 04:30 | 1900-01-04 04:30 | 1900-01-04 04:30 | 1900-01-04 04:30 | 1900-01-04 04:30 | 1900-01-04 04:30

## Totals
Totals and charts
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | Totals | % Finished
Sprint Planning | 0.20833 | 0.39583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60417 | 1450
Daily Scrum | 0.22917 | 0.39583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.625 | 1500
Sprint Review | 0 | 0.10417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10417 | 250
Lectures/Plenary meetings | 0.29167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29167 | 700
Sprint Task 0. Administration | 0.39583 | 0.52083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91667 | 2200
Sprint Task 1. Create website | 0.25 | 0.45833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70833 | 1700
Sprint Task 2. Create visualization 1 | 0.16667 | 0.29167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45833 | 1100
Sprint Task 3. Allow for data upload | 0.20833 | 0.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58333 | 1400
Sprint Task 4. Create draft interim report | 0 | 0.041667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041667 | 100
Sprint Task 5. Create visualization 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task 6. Add interactions | 0 | 0.041667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041667 | 100
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Task x.x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | Totals
David | 0.22917 | 0.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91667
Georgi | 0.1875 | 0.27083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45833
Jeroen | 0.35417 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6875
Julek | 0.41667 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85417
Sasha | 0.29167 | 0.52083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8125
Theo | 0.27083 | 0.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64583
Total budget | 1899-12-31 18:00 | 1900-01-01 15:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900-01-03 09:00
Formulas:
Totals = SUM([week1]:[week10])